## KPI
Contractor LOGO |  |  |  | CENTRAL EXPRESSWAY PROJECT | [10 empty] | Consultant LOGO
|  |  |  | PACKAGE - C |  |  |  | NEM Constructions |  |  | 2018-11-11
TIME LINE | [11 empty] | PROJECT OVERVIEW | [9 empty] | Contract | 1 | 1 | 100% | 1 | 100%
|  |  |  | Contract Start |  | 2017-02-01 | Time Elapsed |  | 649 | Forecasted Finish | 2020-11-09 | SECGEMENT |  | MITIGAMA TO KURUNEGALA | [7 empty] | Elapsed | 0.64067 |  | 25% |  | 112%
|  |  |  | Contract Finish |  | 2019-11-10 | % Time Elapsed |  | 64.07% | % Forecasted Finish | 136% |  |  | 59+000 to 64+000 | [7 empty] | Remaining | 0.35933 |  | 75% |  | 0%
|  |  |  | Contract Duration |  | 1013 | Time Remaining /Time Exceeding |  | -364 | Delay | -365 | CONTRACT NO: |  | XXX |  | PROJECT VALUE |  | 45256254256 |  | CLIENT | RDA | Exceeded beyond contract | -0.35933 | 2 | -100% | 2 | 12%
MILESTONE STATUS |  |  |  | MEASURING PARAMETERS | [9 empty] | HSE STATUS | [7 empty] | Forecast | 0.71964 | 3 | 0% | 3 | 28%
Milestone | Contract Completion | Forecast | Var. (days) | SPI SCHEDULE PERFORMANCE INDEX |  |  |  | CPI COST PERFORMANCE INDEX |  |  | ETC ESTIMATE TO COMPLETE | [7 empty] | STATISTICS
Project Start | 2017-02-01 | 2017-04-17 | -75 | [15 empty] | Total Manhours | 1422500
Mobilization Completion | 2019-07-31 | 2019-10-21 | -82 | [15 empty] | FATALITIES | 0
Highway Design Completion | 2019-06-30 | 2019-09-26 | -88 | [15 empty] | LTI | 1
Structural Design Completion | 2018-07-31 | 2018-10-29 | -90 | PROGRESS S-CURVE | [14 empty] | MTC | 0
Road Pavement Completion | 2019-07-14 | 2019-10-07 | -85 | [15 empty] | FIRST AID | 5
Structures Completion | 2019-07-24 | 2019-10-27 | -95 | [15 empty] | ILL HEALTH | 0 |  |  |  |  | Plan | 45.6%
Project Completion | 2019-07-31 | 2019-11-10 | -102 | [15 empty] | NEAR MIS | 3 |  |  |  |  | Actual | 23.18%
PROGRESS DATA | [18 empty] | OBSERVATIONS | 251
[19 empty] | RIR | Nill
[23 empty] | Cost |  | Percentage |  | Previous |  | Difference |  | Weightage |  | Assigned Cost
[23 empty] | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
[14 empty] | RESOURCE CURVE | [7 empty] | Site Possession & Preliminaries | 1190001 | 1190001 | 3.886% | 3.886% |  |  | 3.886% | 3.886% | 5.461% | 1.7 | 1700000
[22 empty] | Design | 4999995 | 4999995 | 16.33% | 16.33% |  |  | 16.33% | 16.33% | 16.06% | 5 | 5000000
[22 empty] | Construction | 7772634 | 906222 | 25.38% | 2.96% |  |  | 25.38% | 2.96% | 75.27% | 23.43 | 23430000
[22 empty] | Handover | 0 | 0 | 0% | 0% |  |  | 0% | 0% | 3.212% | 1 | 1000000
[22 empty] | Total | 13962630 | 7096218 | 45.6% | 23.18% |  |  | 45.6% | 23.18% | 100% | 31.13 | 31130000
[23 empty] | Cost |  | Percentage |  | Previous |  | Difference |  | Weightage |  | Assigned Cost
0 | [22 empty] | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual
[22 empty] | Site Possession & Preliminaries | 1190001 | 1190001 | 3.886% | 3.886% |  |  | 3.886% | 3.886% | 3.886% | 1.19 | 1190000
[22 empty] | Design | 4999995 | 4999995 | 16.33% | 16.33% |  |  | 16.33% | 16.33% | 16.33% | 5 | 5000000
[22 empty] | Earthworks | 2727473 | 459019 | 8.907% | 1.499% |  |  | 8.907% | 1.499% | 19.6% | 6 | 6000000
[22 empty] | Subgrade & Subbase | 410919 | 60345 | 1.342% | 0.1971% |  |  | 1.342% | 0.1971% | 3.266% | 1 | 1000000
PHYSICAL PROGRESS OF CRITICAL AREAS | [12 empty] | ISSUES & AREAS OF CONCERNS | [8 empty] | Pavement | 558358 | 57478 | 1.824% | 0.1877% |  |  | 1.824% | 0.1877% | 4.572% | 1.4 | 1400000
Activity | Plan % | Actual % | Completion Date | Current SPI | Previous SPI | Trend | [6 empty] | ISSUE |  |  |  | RISK CATEGORY | ACTION |  | PROGRESS |  | Structures | 3420484 | 329380 | 11.17% | 1.076% |  |  | 11.17% | 1.076% | 30.7% | 9.4 | 9400000
[13 empty] | Issue 1 |  |  |  | Very High | xxx |  | yyy |  | Drainage | 655400 | 0 | 2.14% | 0% |  |  | 2.14% | 0% | 3.69% | 1.13 | 1130000
Overall Construction | 46.49% | 24.43% |  | 0.52556 | 0.52491 | é | [6 empty] | Issue 2 |  |  |  | Very High | xxx |  | yyy |  | Incidentials | 0 | 0 | 0% | 0% |  |  | 0% | 0% | 14.7% | 4.5 | 4500000
Prelimnaries | 100% | 100% |  | 1 | 0.99672 | é | [6 empty] | Issue 3 |  |  |  | High | xxx |  | yyy |  | Handover | 0 | 0 | 0% | 0% |  |  | 0% | 0% | 3.266% | 1 | 1000000
Mobilization | 100% | 100% |  | 1 | 0.99389 | é | [6 empty] | Issue 4 |  |  |  | High | xxx |  | yyy |  | Total | 13962630 | 7096218 | 45.6% | 23.18% | 0% | 0% | 45.6% | 23.18% | 100% | 30.62 | 30620000
Highway Design | 100% | 100% |  | 1 | 0.99809 | é | [6 empty] | Issue 5 |  |  |  | High | xxx |  | yyy
Structural Design | 100% | 100% |  | 1 | 0.99169 | é | [6 empty] | Issue 6 |  |  |  | Mid | xxx |  | yyy
Possetion of Site | 100% | 100% |  | 1 | 0.99806 | é | [6 empty] | Issue 7 |  |  |  | Low | xxx |  | yyy
Clearing & Grabing | 46.5% | 9.422% |  | 0.20261 | 0.19814 | é | [6 empty] | Issue 8 |  |  |  | Very Low | xxx |  | yyy
Cutting | 45.34% | 7.453% |  | 0.16438 | 0.16019 | é | [6 empty] | Issue 9 |  |  |  | Very Low | xxx |  | yyy
Embankment Filling | 45.34% | 7.453% |  | 0.16438 | 0.5 | ê | [6 empty] | Issue 10 |  |  |  | Very Low | xxx |  | yyy |  |  |  | Handover | 0% | 0%
Subgrade & Subbase | 41.09% | 6.035% |  | 0.14685 | 0.8 | ê | [6 empty] | Issue 11 |  |  |  | Very Low | xxx |  | yyy |  |  |  | Incidencials | 0% | 0%
Wearing Course | 39.88% | 4.106% |  | 0.10294 | 0.0951 | é | [17 empty] | Drainages | 65540000% | 58%
Viaducts | 36.39% | 3.504% |  | 0.096296 | 0.089251 | é | [17 empty] | Overpasses | 85512100% | 36.39%
Box Culverts | 36.39% | 3.504% |  | 0.096296 | 0.09626 | é | [17 empty] | Underpasses | 85512100% | 36.39%
Underpasses | 36.39% | 3.504% |  | 0.096296 | 0.3 | ê | [17 empty] | Box Culverts | 85512100% | 36.39%
Overpasses | 36.39% | 3.504% |  | 0.096296 | 0.096241 | é | [17 empty] | Viaducts | 85512100% | 36.39%
Drainages | 58% | 0% |  | 0 | -0.0087861 | é | [17 empty] | Wearing Course | 55835800% | 39.88%
Incidencials | 0% | 0% |  | n/a | n/a | è | [17 empty] | Subgrade & Subbase | 41091900% | 41.09%
Handover | 0% | 0% |  | n/a | n/a | è | [17 empty] | Embankment Filling | 136024800% | 45.34%
[24 empty] | Cutting | 108819800% | 45.34%
[24 empty] | Clearing & Grabing | 27902700% | 46.5%
[24 empty] | Possetion of Site | 34000100% | 100%
[24 empty] | Structural Design | 149999600% | 100%
[24 empty] | Highway Design | 349999900% | 100%
[24 empty] | Mobilization | 51000100% | 100%
[24 empty] | Prelimnaries | 85000000% | 100%
[24 empty] | Overall Construction | 1447264100% | 46.49%
[22 empty] | Overall Construction |  |  | 14472641 | 31130000 | 0.46491 | 7606225 | 0.24434
[22 empty] | Prelimnaries |  |  | 850000 | 850000 | 1 | 850000 | 1
[22 empty] | Mobilization |  |  | 510001 | 510000 | 1 | 510001 | 1
[22 empty] | Highway Design |  |  | 3499999 | 3500000 | 1 | 3499999 | 1
[22 empty] | Structural Design |  |  | 1499996 | 1500000 | 1 | 1499996 | 1
[22 empty] | Possetion of Site |  |  | 340001 | 340000 | 1 | 340001 | 1
[22 empty] | Clearing & Grabing |  |  | 279027 | 600000 | 0.46504 | 56535 | 0.094225
[22 empty] | Cutting |  |  | 1088198 | 2400000 | 0.45342 | 178882 | 0.074534
[22 empty] | Embankment Filling |  |  | 1360248 | 3000000 | 0.45342 | 223602 | 0.074534
[22 empty] | Subgrade & Subbase |  |  | 410919 | 1000000 | 0.41092 | 60345 | 0.060345
[22 empty] | Wearing Course |  |  | 558358 | 1400000 | 0.39883 | 57478 | 0.041056
[22 empty] | Viaducts |  |  | 855121 | 2350000 | 0.36388 | 82345 | 0.03504
[22 empty] | Box Culverts |  |  | 855121 | 2350000 | 0.36388 | 82345 | 0.03504
[22 empty] | Underpasses |  |  | 855121 | 2350000 | 0.36388 | 82345 | 0.03504
[22 empty] | Overpasses |  |  | 855121 | 2350000 | 0.36388 | 82345 | 0.03504
[22 empty] | Drainages |  |  | 655400 | 1130000 | 0.58 | 0 | 0
[22 empty] | Incidencials |  |  | 0 | 4500000 | 0 | 0 | 0
[22 empty] | Handover |  |  | 0 | 1000000 | 0 | 0 | 0
Formulas:
Forecast = [Contract Completion]+75
Forecast Completion

## Actual
ACTUAL - MONTHLY DISTRIBUTION
Activity ID |  | Activity Name | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01
Total | [6 empty] | 258937 | 589070 | 588993 | 455626 | 418993 | 432960 | 432960 | 418993 | 393879 | 321292 | 332002 | 332002 | 273790 | 303125 | 293347 | 303125 | 293347 | 1163784 | 1719459 | 1696799 | 1753359 | 1696799 | 1753359 | 1753359 | 2181801 | 2361917 | 2285726 | 2250353 | 1679055 | 2391794
A1010 |  | Prelimnaries | 2017-06-01: 91188; 2017-07-01: 100958; 2017-08-01: 97701; 2017-09-01: 100958; 2017-10-01: 97701; 2017-11-01: 100958; 2017-12-01: 100958; 2018-01-01: 97701; 2018-02-01: 61877
A1020 |  | Mobilization | 2017-06-01: 141667; 2017-07-01: 175667; 2017-08-01: 170000; 2017-09-01: 22667
A1130 |  | Highway Design | 2017-07-01: 197087; 2017-08-01: 203883; 2017-09-01: 210680; 2017-10-01: 203883; 2017-11-01: 210680; 2017-12-01: 210680; 2018-01-01: 203883; 2018-02-01: 210680; 2018-03-01: 203883; 2018-04-01: 210680; 2018-05-01: 210680; 2018-06-01: 190291; 2018-07-01: 210680; 2018-08-01: 203883; 2018-09-01: 210680; 2018-10-01: 203883; 2018-11-01: 203883
A1140 |  | Structural Design | 2017-07-01: 86481; 2017-08-01: 89463; 2017-09-01: 92445; 2017-10-01: 89463; 2017-11-01: 92445; 2017-12-01: 92445; 2018-01-01: 89463; 2018-02-01: 92445; 2018-03-01: 89463; 2018-04-01: 92445; 2018-05-01: 92445; 2018-06-01: 83499; 2018-07-01: 92445; 2018-08-01: 89463; 2018-09-01: 92445; 2018-10-01: 89463; 2018-11-01: 53678
A1160 |  | Possetion of Site | 2017-06-01: 26082; 2017-07-01: 28877; 2017-08-01: 27945; 2017-09-01: 28877; 2017-10-01: 27945; 2017-11-01: 28877; 2017-12-01: 28877; 2018-01-01: 27945; 2018-02-01: 28877; 2018-03-01: 27945; 2018-04-01: 28877; 2018-05-01: 28877
A1030 |  | Clearing & Grabing | 2018-11-01: 56535; 2018-12-01: 56535; 2019-01-01: 54711; 2019-02-01: 56535; 2019-03-01: 54711; 2019-04-01: 56535; 2019-05-01: 56535; 2019-06-01: 51064; 2019-07-01: 56535; 2019-08-01: 54711; 2019-09-01: 45593
A1040 |  | Cutting | 2018-11-01: 178882; 2018-12-01: 231056; 2019-01-01: 223602; 2019-02-01: 231056; 2019-03-01: 223602; 2019-04-01: 231056; 2019-05-01: 231056; 2019-06-01: 208696; 2019-07-01: 231056; 2019-08-01: 223602; 2019-09-01: 186335
A1050 |  | Embankment Filling | 2018-11-01: 223602; 2018-12-01: 288820; 2019-01-01: 279503; 2019-02-01: 288820; 2019-03-01: 279503; 2019-04-01: 288820; 2019-05-01: 288820; 2019-06-01: 260870; 2019-07-01: 288820; 2019-08-01: 279503; 2019-09-01: 232919
A1000 |  | Subgrade & Subbase | 2018-11-01: 60345; 2018-12-01: 89080; 2019-01-01: 86207; 2019-02-01: 89080; 2019-03-01: 86207; 2019-04-01: 89080; 2019-05-01: 89080; 2019-06-01: 80460; 2019-07-01: 89080; 2019-08-01: 86207; 2019-09-01: 89080; 2019-10-01: 66092
A1060 |  | Wearing Course | 2018-11-01: 57478; 2018-12-01: 127273; 2019-01-01: 123167; 2019-02-01: 127273; 2019-03-01: 123167; 2019-04-01: 127273; 2019-05-01: 127273; 2019-06-01: 114956; 2019-07-01: 127273; 2019-08-01: 123167; 2019-09-01: 127273; 2019-10-01: 94428
A1070 |  | Viaducts | 2018-11-01: 82345; 2018-12-01: 196361; 2019-01-01: 190027; 2019-02-01: 196361; 2019-03-01: 190027; 2019-04-01: 196361; 2019-05-01: 196361; 2019-06-01: 177358; 2019-07-01: 196361; 2019-08-01: 190027; 2019-09-01: 196361; 2019-10-01: 190027; 2019-11-01: 152022
A1080 |  | Box Culverts | 2018-11-01: 82345; 2018-12-01: 196361; 2019-01-01: 190027; 2019-02-01: 196361; 2019-03-01: 190027; 2019-04-01: 196361; 2019-05-01: 196361; 2019-06-01: 177358; 2019-07-01: 196361; 2019-08-01: 190027; 2019-09-01: 196361; 2019-10-01: 190027; 2019-11-01: 152022
A1090 |  | Underpasses | 2018-11-01: 82345; 2018-12-01: 196361; 2019-01-01: 190027; 2019-02-01: 196361; 2019-03-01: 190027; 2019-04-01: 196361; 2019-05-01: 196361; 2019-06-01: 177358; 2019-07-01: 196361; 2019-08-01: 190027; 2019-09-01: 196361; 2019-10-01: 190027; 2019-11-01: 152022
A1100 |  | Overpasses | 2018-11-01: 82345; 2018-12-01: 196361; 2019-01-01: 190027; 2019-02-01: 196361; 2019-03-01: 190027; 2019-04-01: 196361; 2019-05-01: 196361; 2019-06-01: 177358; 2019-07-01: 196361; 2019-08-01: 190027; 2019-09-01: 196361; 2019-10-01: 190027; 2019-11-01: 152022
A1190 |  | Drainages | 2018-12-01: 141250; 2019-01-01: 169500; 2019-02-01: 175150; 2019-03-01: 169500; 2019-04-01: 175150; 2019-05-01: 175150; 2019-06-01: 124300
A1120 |  | Incidencials | 2019-06-01: 632022; 2019-07-01: 783708; 2019-08-01: 758427; 2019-09-01: 783708; 2019-10-01: 758427; 2019-11-01: 783708
A1170 |  | Handover | 2019-11-01: 1000000
ACTUAL - CUMULATIVE MONTHLY DISTRIBUTION
Activity ID |  | Activity Name | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01
Total | [6 empty] | 258937 | 848007 | 1437000 | 1892626 | 2311619 | 2744579 | 3177539 | 3596532 | 3990411 | 4311703 | 4643705 | 4975707 | 5249497 | 5552622 | 5845969 | 6149094 | 6442441 | 7606225 | 9325684 | 11022483 | 12775842 | 14472641 | 16226000 | 17979359 | 20161160 | 22523077 | 24808803 | 27059156 | 28738211 | 31130005
A1010 |  | Prelimnaries |  |  |  |  | 91188 | 192146 | 289847 | 390805 | 488506 | 589464 | 690422 | 788123 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000
A1020 |  | Mobilization |  |  |  |  | 141667 | 317334 | 487334 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001
A1130 |  | Highway Design |  |  |  |  | 0 | 197087 | 400970 | 611650 | 815533 | 1026213 | 1236893 | 1440776 | 1651456 | 1855339 | 2066019 | 2276699 | 2466990 | 2677670 | 2881553 | 3092233 | 3296116 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999
A1140 |  | Structural Design |  |  |  |  | 0 | 86481 | 175944 | 268389 | 357852 | 450297 | 542742 | 632205 | 724650 | 814113 | 906558 | 999003 | 1082502 | 1174947 | 1264410 | 1356855 | 1446318 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996
A1160 |  | Possetion of Site |  |  |  |  | 26082 | 54959 | 82904 | 111781 | 139726 | 168603 | 197480 | 225425 | 254302 | 282247 | 311124 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001
A1030 |  | Clearing & Grabing |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56535 | 113070 | 167781 | 224316 | 279027 | 335562 | 392097 | 443161 | 499696 | 554407 | 600000 | 600000 | 600000
A1040 |  | Cutting |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178882 | 409938 | 633540 | 864596 | 1088198 | 1319254 | 1550310 | 1759006 | 1990062 | 2213664 | 2399999 | 2399999 | 2399999
A1050 |  | Embankment Filling |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223602 | 512422 | 791925 | 1080745 | 1360248 | 1649068 | 1937888 | 2198758 | 2487578 | 2767081 | 3000000 | 3000000 | 3000000
A1000 |  | Subgrade & Subbase |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60345 | 149425 | 235632 | 324712 | 410919 | 499999 | 589079 | 669539 | 758619 | 844826 | 933906 | 999998 | 999998
A1060 |  | Wearing Course |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57478 | 184751 | 307918 | 435191 | 558358 | 685631 | 812904 | 927860 | 1055133 | 1178300 | 1305573 | 1400001 | 1400001
A1070 |  | Viaducts |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82345 | 278706 | 468733 | 665094 | 855121 | 1051482 | 1247843 | 1425201 | 1621562 | 1811589 | 2007950 | 2197977 | 2349999
A1080 |  | Box Culverts |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82345 | 278706 | 468733 | 665094 | 855121 | 1051482 | 1247843 | 1425201 | 1621562 | 1811589 | 2007950 | 2197977 | 2349999
A1090 |  | Underpasses |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82345 | 278706 | 468733 | 665094 | 855121 | 1051482 | 1247843 | 1425201 | 1621562 | 1811589 | 2007950 | 2197977 | 2349999
A1100 |  | Overpasses |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82345 | 278706 | 468733 | 665094 | 855121 | 1051482 | 1247843 | 1425201 | 1621562 | 1811589 | 2007950 | 2197977 | 2349999
A1190 |  | Drainages |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141250 | 310750 | 485900 | 655400 | 830550 | 1005700 | 1130000 | 1130000 | 1130000 | 1130000 | 1130000 | 1130000
A1120 |  | Incidencials |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632022 | 1415730 | 2174157 | 2957865 | 3716292 | 4500000
A1170 |  | Handover |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
ACTUAL - CUMULATIVE MONTHLY DISTRIBUTION | Actual
Activity ID |  | Activity Name | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01
Total |  |  | 0% | 0% | 0% | 0% | 0.8318% | 2.724% | 4.616% | 6.08% | 7.426% | 8.817% | 10.21% | 11.55% | 12.82% | 13.85% | 14.92% | 15.98% | 16.86% | 17.84% | 18.78% | 19.75% | 20.7% | 24.43%
A1010 |  | Prelimnaries | 0% | 0% | 0% | 0% | 0.2929% | 0.6172% | 0.9311% | 1.255% | 1.569% | 1.894% | 2.218% | 2.532% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73%
A1020 |  | Mobilization | 0% | 0% | 0% | 0% | 0.4551% | 1.019% | 1.565% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638%
A1130 |  | Highway Design | 0% | 0% | 0% | 0% | 0% | 0.6331% | 1.288% | 1.965% | 2.62% | 3.297% | 3.973% | 4.628% | 5.305% | 5.96% | 6.637% | 7.314% | 7.925% | 8.602% | 9.257% | 9.933% | 10.59% | 11.24%
A1140 |  | Structural Design | 0% | 0% | 0% | 0% | 0% | 0.2778% | 0.5652% | 0.8622% | 1.15% | 1.447% | 1.743% | 2.031% | 2.328% | 2.615% | 2.912% | 3.209% | 3.477% | 3.774% | 4.062% | 4.359% | 4.646% | 4.818%
A1160 |  | Possetion of Site | 0% | 0% | 0% | 0% | 0.08378% | 0.1765% | 0.2663% | 0.3591% | 0.4488% | 0.5416% | 0.6344% | 0.7241% | 0.8169% | 0.9067% | 0.9994% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092%
A1030 |  | Clearing & Grabing | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1816%
A1040 |  | Cutting | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5746%
A1050 |  | Embankment Filling | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7183%
A1000 |  | Subgrade & Subbase | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1938%
A1060 |  | Wearing Course | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1846%
A1070 |  | Viaducts | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2645%
A1080 |  | Box Culverts | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2645%
A1090 |  | Underpasses | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2645%
A1100 |  | Overpasses | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2645%
A1190 |  | Drainages | bar: 2017-02-01 to 2018-11-01
A1120 |  | Incidencials | bar: 2017-02-01 to 2018-11-01
A1170 |  | Handover | bar: 2017-02-01 to 2018-11-01

## Baseline
WBS LEVEL 3
BASELINE - MONTHLY DISTRIBUTION | Baseline
Activity ID |  | Activity Name | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 43617 | 43647 | 2019-08-01
Total |  |  | 258937 | 589070 | 588993 | 455626 | 418993 | 432960 | 432960 | 418993 | 393879 | 321292 | 332002 | 332002 | 273790 | 303125 | 293347 | 303125 | 293347 | 1163784 | 1719459 | 1696799 | 1753359 | 1696799 | 1753359 | 1753359 | 2181801 | 2361917 | 2285726 | 2250353 | 1679055 | 2391794
A1010 |  | Prelimnaries | 91188 | 100958 | 97701 | 100958 | 97701 | 100958 | 100958 | 97701 | 61877
A1020 |  | Mobilization | 141667 | 175667 | 170000 | 22667
A1130 |  | Highway Design |  | 197087 | 203883 | 210680 | 203883 | 210680 | 210680 | 203883 | 210680 | 203883 | 210680 | 210680 | 190291 | 210680 | 203883 | 210680 | 203883 | 203883
A1140 |  | Structural Design |  | 86481 | 89463 | 92445 | 89463 | 92445 | 92445 | 89463 | 92445 | 89463 | 92445 | 92445 | 83499 | 92445 | 89463 | 92445 | 89463 | 53678
A1160 |  | Possetion of Site | 26082 | 28877 | 27945 | 28877 | 27945 | 28877 | 28877 | 27945 | 28877 | 27945 | 28877 | 28877
A1030 |  | Clearing & Grabing | [17 empty] | 56535 | 56535 | 54711 | 56535 | 54711 | 56535 | 56535 | 51064 | 56535 | 54711 | 45593
A1040 |  | Cutting | [17 empty] | 178882 | 231056 | 223602 | 231056 | 223602 | 231056 | 231056 | 208696 | 231056 | 223602 | 186335
A1050 |  | Embankment Filling | [17 empty] | 223602 | 288820 | 279503 | 288820 | 279503 | 288820 | 288820 | 260870 | 288820 | 279503 | 232919
A1000 |  | Subgrade & Subbase | [17 empty] | 60345 | 89080 | 86207 | 89080 | 86207 | 89080 | 89080 | 80460 | 89080 | 86207 | 89080 | 66092
A1060 |  | Wearing Course | [17 empty] | 57478 | 127273 | 123167 | 127273 | 123167 | 127273 | 127273 | 114956 | 127273 | 123167 | 127273 | 94428
A1070 |  | Viaducts | [17 empty] | 82345 | 196361 | 190027 | 196361 | 190027 | 196361 | 196361 | 177358 | 196361 | 190027 | 196361 | 190027 | 152022
A1080 |  | Box Culverts | [17 empty] | 82345 | 196361 | 190027 | 196361 | 190027 | 196361 | 196361 | 177358 | 196361 | 190027 | 196361 | 190027 | 152022
A1090 |  | Underpasses | [17 empty] | 82345 | 196361 | 190027 | 196361 | 190027 | 196361 | 196361 | 177358 | 196361 | 190027 | 196361 | 190027 | 152022
A1100 |  | Overpasses | [17 empty] | 82345 | 196361 | 190027 | 196361 | 190027 | 196361 | 196361 | 177358 | 196361 | 190027 | 196361 | 190027 | 152022
A1190 |  | Drainages | [18 empty] | 141250 | 169500 | 175150 | 169500 | 175150 | 175150 | 124300
A1120 |  | Incidencials | [24 empty] | 632022 | 783708 | 758427 | 783708 | 758427 | 783708
A1170 |  | Handover | [29 empty] | 1000000
BASELINE - CUMULATIVE MONTHLY DISTRIBUTION | Baseline
Activity ID | 1 | Activity Name | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 43617 | 43647 | 2019-08-01
Total | 2 |  | 258937 | 848007 | 1437000 | 1892626 | 2311619 | 2744579 | 3177539 | 3596532 | 3990411 | 4311703 | 4643705 | 4975707 | 5249497 | 5552622 | 5845969 | 6149094 | 6442441 | 7606225 | 9325684 | 11022483 | 12775842 | 14472641 | 16226000 | 17979359 | 20161160 | 22523077 | 24808803 | 27059156 | 28738211 | 31130005
A1010 | 3 | Prelimnaries | 91188 | 192146 | 289847 | 390805 | 488506 | 589464 | 690422 | 788123 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000
A1020 | 4 | Mobilization | 141667 | 317334 | 487334 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001
A1130 | 5 | Highway Design | 0 | 197087 | 400970 | 611650 | 815533 | 1026213 | 1236893 | 1440776 | 1651456 | 1855339 | 2066019 | 2276699 | 2466990 | 2677670 | 2881553 | 3092233 | 3296116 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999 | 3499999
A1140 | 6 | Structural Design | 0 | 86481 | 175944 | 268389 | 357852 | 450297 | 542742 | 632205 | 724650 | 814113 | 906558 | 999003 | 1082502 | 1174947 | 1264410 | 1356855 | 1446318 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996 | 1499996
A1160 | 7 | Possetion of Site | 26082 | 54959 | 82904 | 111781 | 139726 | 168603 | 197480 | 225425 | 254302 | 282247 | 311124 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001
A1030 | 8 | Clearing & Grabing | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 56535 | 113070 | 167781 | 224316 | 279027 | 335562 | 392097 | 443161 | 499696 | 554407 | 600000 | 600000 | 600000
A1040 | 9 | Cutting | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178882 | 409938 | 633540 | 864596 | 1088198 | 1319254 | 1550310 | 1759006 | 1990062 | 2213664 | 2399999 | 2399999 | 2399999
A1050 | 10 | Embankment Filling | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 223602 | 512422 | 791925 | 1080745 | 1360248 | 1649068 | 1937888 | 2198758 | 2487578 | 2767081 | 3000000 | 3000000 | 3000000
A1000 | 11 | Subgrade & Subbase | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60345 | 149425 | 235632 | 324712 | 410919 | 499999 | 589079 | 669539 | 758619 | 844826 | 933906 | 999998 | 999998
A1060 | 12 | Wearing Course | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57478 | 184751 | 307918 | 435191 | 558358 | 685631 | 812904 | 927860 | 1055133 | 1178300 | 1305573 | 1400001 | 1400001
A1070 | 13 | Viaducts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82345 | 278706 | 468733 | 665094 | 855121 | 1051482 | 1247843 | 1425201 | 1621562 | 1811589 | 2007950 | 2197977 | 2349999
A1080 | 14 | Box Culverts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82345 | 278706 | 468733 | 665094 | 855121 | 1051482 | 1247843 | 1425201 | 1621562 | 1811589 | 2007950 | 2197977 | 2349999
A1090 | 15 | Underpasses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82345 | 278706 | 468733 | 665094 | 855121 | 1051482 | 1247843 | 1425201 | 1621562 | 1811589 | 2007950 | 2197977 | 2349999
A1100 | 16 | Overpasses | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82345 | 278706 | 468733 | 665094 | 855121 | 1051482 | 1247843 | 1425201 | 1621562 | 1811589 | 2007950 | 2197977 | 2349999
A1190 | 17 | Drainages | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141250 | 310750 | 485900 | 655400 | 830550 | 1005700 | 1130000 | 1130000 | 1130000 | 1130000 | 1130000 | 1130000
A1120 | 18 | Incidencials | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632022 | 1415730 | 2174157 | 2957865 | 3716292 | 4500000
A1170 | 19 | Handover | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
BASELINE -% CUMULATIVE MONTHLY DISTRIBUTION | Baseline
Activity ID | 1 | Activity Name | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 43617 | 43647 | 2019-08-01
Total | 2 |  | 0.8318% | 2.724% | 4.616% | 6.08% | 7.426% | 8.817% | 10.21% | 11.55% | 12.82% | 13.85% | 14.92% | 15.98% | 16.86% | 17.84% | 18.78% | 19.75% | 20.7% | 24.43% | 29.96% | 35.41% | 41.04% | 46.49% | 52.12% | 57.76% | 64.76% | 72.35% | 79.69% | 86.92% | 92.32% | 100%
A1010 | 3 | Prelimnaries | 0.2929% | 0.6172% | 0.9311% | 1.255% | 1.569% | 1.894% | 2.218% | 2.532% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73% | 2.73%
A1020 | 4 | Mobilization | 0.4551% | 1.019% | 1.565% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638% | 1.638%
A1130 | 5 | Highway Design | 0% | 0.6331% | 1.288% | 1.965% | 2.62% | 3.297% | 3.973% | 4.628% | 5.305% | 5.96% | 6.637% | 7.314% | 7.925% | 8.602% | 9.257% | 9.933% | 10.59% | 11.24% | 11.24% | 11.24% | 11.24% | 11.24% | 11.24% | 11.24% | 11.24% | 11.24% | 11.24% | 11.24% | 11.24% | 11.24%
A1140 | 6 | Structural Design | 0% | 0.2778% | 0.5652% | 0.8622% | 1.15% | 1.447% | 1.743% | 2.031% | 2.328% | 2.615% | 2.912% | 3.209% | 3.477% | 3.774% | 4.062% | 4.359% | 4.646% | 4.818% | 4.818% | 4.818% | 4.818% | 4.818% | 4.818% | 4.818% | 4.818% | 4.818% | 4.818% | 4.818% | 4.818% | 4.818%
A1160 | 7 | Possetion of Site | 0.08378% | 0.1765% | 0.2663% | 0.3591% | 0.4488% | 0.5416% | 0.6344% | 0.7241% | 0.8169% | 0.9067% | 0.9994% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092% | 1.092%
A1030 | 8 | Clearing & Grabing | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1816% | 0.3632% | 0.539% | 0.7206% | 0.8963% | 1.078% | 1.26% | 1.424% | 1.605% | 1.781% | 1.927% | 1.927% | 1.927%
A1040 | 9 | Cutting | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.5746% | 1.317% | 2.035% | 2.777% | 3.496% | 4.238% | 4.98% | 5.651% | 6.393% | 7.111% | 7.71% | 7.71% | 7.71%
A1050 | 10 | Embankment Filling | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.7183% | 1.646% | 2.544% | 3.472% | 4.37% | 5.297% | 6.225% | 7.063% | 7.991% | 8.889% | 9.637% | 9.637% | 9.637%
A1000 | 11 | Subgrade & Subbase | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1938% | 0.48% | 0.7569% | 1.043% | 1.32% | 1.606% | 1.892% | 2.151% | 2.437% | 2.714% | 3% | 3.212% | 3.212%
A1060 | 12 | Wearing Course | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.1846% | 0.5935% | 0.9891% | 1.398% | 1.794% | 2.202% | 2.611% | 2.981% | 3.389% | 3.785% | 4.194% | 4.497% | 4.497%
A1070 | 13 | Viaducts | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2645% | 0.8953% | 1.506% | 2.137% | 2.747% | 3.378% | 4.008% | 4.578% | 5.209% | 5.819% | 6.45% | 7.061% | 7.549%
A1080 | 14 | Box Culverts | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2645% | 0.8953% | 1.506% | 2.137% | 2.747% | 3.378% | 4.008% | 4.578% | 5.209% | 5.819% | 6.45% | 7.061% | 7.549%
A1090 | 15 | Underpasses | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2645% | 0.8953% | 1.506% | 2.137% | 2.747% | 3.378% | 4.008% | 4.578% | 5.209% | 5.819% | 6.45% | 7.061% | 7.549%
A1100 | 16 | Overpasses | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2645% | 0.8953% | 1.506% | 2.137% | 2.747% | 3.378% | 4.008% | 4.578% | 5.209% | 5.819% | 6.45% | 7.061% | 7.549%
A1190 | 17 | Drainages | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.4537% | 0.9982% | 1.561% | 2.105% | 2.668% | 3.231% | 3.63% | 3.63% | 3.63% | 3.63% | 3.63% | 3.63%
A1120 | 18 | Incidencials | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.03% | 4.548% | 6.984% | 9.502% | 11.94% | 14.46%
A1170 | 19 | Handover | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.212%

## Level1 (hidden)
WBS LEVEL 2
BASELINE - MONTHLY DISTRIBUTION
Activity ID | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01
Total | 258937 | 589070 | 588993 | 455626 | 418993 | 432960 | 432960 | 418993 | 393879 | 321292 | 332002 | 332002 | 273790 | 303125 | 293347 | 303125 | 293347 | 1163784 | 1719459 | 1696799 | 1753359 | 1696799 | 1753359 | 1753359 | 2181801 | 2361917 | 2285726 | 2250353 | 1679055 | 2391794
WBS: PACKAGE C.5 PRELIMINARIES | 2017-02-01: 91188; 2017-03-01: 100958; 2017-04-01: 97701; 2017-05-01: 100958; 2017-06-01: 97701; 2017-07-01: 100958; 2017-08-01: 100958; 2017-09-01: 97701; 2017-10-01: 61877
WBS: PACKAGE C.9 MOBILIZATION | 2017-02-01: 141667; 2017-03-01: 175667; 2017-04-01: 170000; 2017-05-01: 22667
WBS: PACKAGE C.1 DESIGN | 2017-03-01: 283568; 2017-04-01: 293347; 2017-05-01: 303125; 2017-06-01: 293347; 2017-07-01: 303125; 2017-08-01: 303125; 2017-09-01: 293347; 2017-10-01: 303125; 2017-11-01: 293347; 2017-12-01: 303125; 2018-01-01: 303125; 2018-02-01: 273790; 2018-03-01: 303125; 2018-04-01: 293347; 2018-05-01: 303125; 2018-06-01: 293347; 2018-07-01: 257561
WBS: PACKAGE C.2 SITE POSSESSION | 2017-02-01: 26082; 2017-03-01: 28877; 2017-04-01: 27945; 2017-05-01: 28877; 2017-06-01: 27945; 2017-07-01: 28877; 2017-08-01: 28877; 2017-09-01: 27945; 2017-10-01: 28877; 2017-11-01: 27945; 2017-12-01: 28877; 2018-01-01: 28877
WBS: PACKAGE C.10 EARTH WORKS | 2018-07-01: 459019; 2018-08-01: 576411; 2018-09-01: 557817; 2018-10-01: 576411; 2018-11-01: 557817; 2018-12-01: 576411; 2019-01-01: 576411; 2019-02-01: 520629; 2019-03-01: 576411; 2019-04-01: 557817; 2019-05-01: 464847
WBS: PACKAGE C.6 SUB-GRADE & SUB-BASE | 2018-07-01: 60345; 2018-08-01: 89080; 2018-09-01: 86207; 2018-10-01: 89080; 2018-11-01: 86207; 2018-12-01: 89080; 2019-01-01: 89080; 2019-02-01: 80460; 2019-03-01: 89080; 2019-04-01: 86207; 2019-05-01: 89080; 2019-06-01: 66092
WBS: PACKAGE C.11 PAVEMENT | 2018-07-01: 57478; 2018-08-01: 127273; 2018-09-01: 123167; 2018-10-01: 127273; 2018-11-01: 123167; 2018-12-01: 127273; 2019-01-01: 127273; 2019-02-01: 114956; 2019-03-01: 127273; 2019-04-01: 123167; 2019-05-01: 127273; 2019-06-01: 94428
WBS: PACKAGE C.7 STRUCTURES | 2018-07-01: 329380; 2018-08-01: 785445; 2018-09-01: 760108; 2018-10-01: 785445; 2018-11-01: 760108; 2018-12-01: 785445; 2019-01-01: 785445; 2019-02-01: 709434; 2019-03-01: 785445; 2019-04-01: 760108; 2019-05-01: 785445; 2019-06-01: 760108; 2019-07-01: 608086
WBS: PACKAGE C.12 DRAINAGE | 2018-08-01: 141250; 2018-09-01: 169500; 2018-10-01: 175150; 2018-11-01: 169500; 2018-12-01: 175150; 2019-01-01: 175150; 2019-02-01: 124300
WBS: PACKAGE C.3 INCIDENCIALS | 2019-02-01: 632022; 2019-03-01: 783708; 2019-04-01: 758427; 2019-05-01: 783708; 2019-06-01: 758427; 2019-07-01: 783708
WBS: PACKAGE C.4 HANDOVER | 2019-07-01: 1000000
BASELINE - CUMULATIVE MONTHLY DISTRIBUTION
Activity ID | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01
Total | 258937 | 848007 | 1437000 | 1892626 | 2311619 | 2744579 | 3177539 | 3596532 | 3990411 | 4311703 | 4643705 | 4975707 | 5249497 | 5552622 | 5845969 | 6149094 | 6442441 | 7606225 | 9325684 | 11022483 | 12775842 | 14472641 | 16226000 | 17979359 | 20161160 | 22523077 | 24808803 | 27059156 | 28738211 | 31130005
WBS: PACKAGE C.5 PRELIMINARIES | 91188 | 192146 | 289847 | 390805 | 488506 | 589464 | 690422 | 788123 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000
WBS: PACKAGE C.9 MOBILIZATION | 141667 | 317334 | 487334 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001
WBS: PACKAGE C.1 DESIGN | 0 | 283568 | 576915 | 880040 | 1173387 | 1476512 | 1779637 | 2072984 | 2376109 | 2669456 | 2972581 | 3275706 | 3549496 | 3852621 | 4145968 | 4449093 | 4742440 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001
WBS: PACKAGE C.2 SITE POSSESSION | 26082 | 54959 | 82904 | 111781 | 139726 | 168603 | 197480 | 225425 | 254302 | 282247 | 311124 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001
WBS: PACKAGE C.10 EARTH WORKS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459019 | 1035430 | 1593247 | 2169658 | 2727475 | 3303886 | 3880297 | 4400926 | 4977337 | 5535154 | 6000001 | 6000001 | 6000001
WBS: PACKAGE C.6 SUB-GRADE & SUB-BASE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60345 | 149425 | 235632 | 324712 | 410919 | 499999 | 589079 | 669539 | 758619 | 844826 | 933906 | 999998 | 999998
WBS: PACKAGE C.11 PAVEMENT | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57478 | 184751 | 307918 | 435191 | 558358 | 685631 | 812904 | 927860 | 1055133 | 1178300 | 1305573 | 1400001 | 1400001
WBS: PACKAGE C.7 STRUCTURES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329380 | 1114825 | 1874933 | 2660378 | 3420486 | 4205931 | 4991376 | 5700810 | 6486255 | 7246363 | 8031808 | 8791916 | 9400002
WBS: PACKAGE C.12 DRAINAGE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141250 | 310750 | 485900 | 655400 | 830550 | 1005700 | 1130000 | 1130000 | 1130000 | 1130000 | 1130000 | 1130000
WBS: PACKAGE C.3 INCIDENCIALS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632022 | 1415730 | 2174157 | 2957865 | 3716292 | 4500000
WBS: PACKAGE C.4 HANDOVER | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000
ACTUAL - MONTHLY DISTRIBUTION
Activity ID | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01
Total |  |  |  |  | 258937 | 589070 | 588993 | 455626 | 418993 | 432960 | 432960 | 418993 | 393879 | 321292 | 332002 | 332002 | 273790 | 303125 | 293347 | 303125 | 293347 | 1163784 | 1719459 | 1696799 | 1753359 | 1696799 | 1753359 | 1753359 | 2181801 | 2361917 | 2285726 | 2250353 | 1679055 | 2391794
WBS: PACKAGE C.5 PRELIMINARIES | 2017-06-01: 91188; 2017-07-01: 100958; 2017-08-01: 97701; 2017-09-01: 100958; 2017-10-01: 97701; 2017-11-01: 100958; 2017-12-01: 100958; 2018-01-01: 97701; 2018-02-01: 61877
WBS: PACKAGE C.9 MOBILIZATION | 2017-06-01: 141667; 2017-07-01: 175667; 2017-08-01: 170000; 2017-09-01: 22667
WBS: PACKAGE C.1 DESIGN | 2017-07-01: 283568; 2017-08-01: 293347; 2017-09-01: 303125; 2017-10-01: 293347; 2017-11-01: 303125; 2017-12-01: 303125; 2018-01-01: 293347; 2018-02-01: 303125; 2018-03-01: 293347; 2018-04-01: 303125; 2018-05-01: 303125; 2018-06-01: 273790; 2018-07-01: 303125; 2018-08-01: 293347; 2018-09-01: 303125; 2018-10-01: 293347; 2018-11-01: 257561
WBS: PACKAGE C.2 SITE POSSESSION | 2017-06-01: 26082; 2017-07-01: 28877; 2017-08-01: 27945; 2017-09-01: 28877; 2017-10-01: 27945; 2017-11-01: 28877; 2017-12-01: 28877; 2018-01-01: 27945; 2018-02-01: 28877; 2018-03-01: 27945; 2018-04-01: 28877; 2018-05-01: 28877
WBS: PACKAGE C.10 EARTH WORKS | 2018-11-01: 459019; 2018-12-01: 576411; 2019-01-01: 557817; 2019-02-01: 576411; 2019-03-01: 557817; 2019-04-01: 576411; 2019-05-01: 576411; 2019-06-01: 520629; 2019-07-01: 576411; 2019-08-01: 557817; 2019-09-01: 464847
WBS: PACKAGE C.6 SUB-GRADE & SUB-BASE | 2018-11-01: 60345; 2018-12-01: 89080; 2019-01-01: 86207; 2019-02-01: 89080; 2019-03-01: 86207; 2019-04-01: 89080; 2019-05-01: 89080; 2019-06-01: 80460; 2019-07-01: 89080; 2019-08-01: 86207; 2019-09-01: 89080; 2019-10-01: 66092
WBS: PACKAGE C.11 PAVEMENT | 2018-11-01: 57478; 2018-12-01: 127273; 2019-01-01: 123167; 2019-02-01: 127273; 2019-03-01: 123167; 2019-04-01: 127273; 2019-05-01: 127273; 2019-06-01: 114956; 2019-07-01: 127273; 2019-08-01: 123167; 2019-09-01: 127273; 2019-10-01: 94428
WBS: PACKAGE C.7 STRUCTURES | 2018-11-01: 329380; 2018-12-01: 785445; 2019-01-01: 760108; 2019-02-01: 785445; 2019-03-01: 760108; 2019-04-01: 785445; 2019-05-01: 785445; 2019-06-01: 709434; 2019-07-01: 785445; 2019-08-01: 760108; 2019-09-01: 785445; 2019-10-01: 760108; 2019-11-01: 608086
WBS: PACKAGE C.12 DRAINAGE | 2018-12-01: 141250; 2019-01-01: 169500; 2019-02-01: 175150; 2019-03-01: 169500; 2019-04-01: 175150; 2019-05-01: 175150; 2019-06-01: 124300
WBS: PACKAGE C.3 INCIDENCIALS | 2019-06-01: 632022; 2019-07-01: 783708; 2019-08-01: 758427; 2019-09-01: 783708; 2019-10-01: 758427; 2019-11-01: 783708
WBS: PACKAGE C.4 HANDOVER | 2019-11-01: 1000000
ACTUAL - CUMULATIVE MONTHLY DISTRIBUTION
Activity ID | 2017-02-01 | 2017-03-01 | 2017-04-01 | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01
Total |  |  |  |  | 258937 | 848007 | 1437000 | 1892626 | 2311619 | 2744579 | 3177539 | 3596532 | 3990411 | 4311703 | 4643705 | 4975707 | 5249497 | 5552622 | 5845969 | 6149094 | 6442441 | 7606225 | 9325684 | 11022483 | 12775842 | 14472641 | 16226000 | 17979359 | 20161160 | 22523077 | 24808803 | 27059156 | 28738211 | 31130005
WBS: PACKAGE C.5 PRELIMINARIES |  |  |  |  | 91188 | 192146 | 289847 | 390805 | 488506 | 589464 | 690422 | 788123 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000 | 850000
WBS: PACKAGE C.9 MOBILIZATION |  |  |  |  | 141667 | 317334 | 487334 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001 | 510001
WBS: PACKAGE C.1 DESIGN |  |  |  |  | 0 | 283568 | 576915 | 880040 | 1173387 | 1476512 | 1779637 | 2072984 | 2376109 | 2669456 | 2972581 | 3275706 | 3549496 | 3852621 | 4145968 | 4449093 | 4742440 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001 | 5000001
WBS: PACKAGE C.2 SITE POSSESSION |  |  |  |  | 26082 | 54959 | 82904 | 111781 | 139726 | 168603 | 197480 | 225425 | 254302 | 282247 | 311124 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001 | 340001
WBS: PACKAGE C.10 EARTH WORKS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 459019 | 1035430 | 1593247 | 2169658 | 2727475 | 3303886 | 3880297 | 4400926 | 4977337 | 5535154 | 6000001 | 6000001 | 6000001
WBS: PACKAGE C.6 SUB-GRADE & SUB-BASE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60345 | 149425 | 235632 | 324712 | 410919 | 499999 | 589079 | 669539 | 758619 | 844826 | 933906 | 999998 | 999998
WBS: PACKAGE C.11 PAVEMENT |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57478 | 184751 | 307918 | 435191 | 558358 | 685631 | 812904 | 927860 | 1055133 | 1178300 | 1305573 | 1400001 | 1400001
WBS: PACKAGE C.7 STRUCTURES |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 329380 | 1114825 | 1874933 | 2660378 | 3420486 | 4205931 | 4991376 | 5700810 | 6486255 | 7246363 | 8031808 | 8791916 | 9400002
WBS: PACKAGE C.12 DRAINAGE |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 141250 | 310750 | 485900 | 655400 | 830550 | 1005700 | 1130000 | 1130000 | 1130000 | 1130000 | 1130000 | 1130000
WBS: PACKAGE C.3 INCIDENCIALS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 632022 | 1415730 | 2174157 | 2957865 | 3716292 | 4500000
WBS: PACKAGE C.4 HANDOVER |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000000

## Cost Assignment
|  | 31130000 | 31130000
Activity ID | Activity Name
Package C
MILESTONES
A1150 | Project Start
A1180 | Project Finish
PRELIMINARIES
A1010 | Prelimnaries | 850000 | 850000
MOBILIZATION
A1020 | Mobilization | 510000 | 510000
DESIGN
A1130 | Highway Design | 3500000 | 3500000
A1140 | Structural Design | 1500000 | 1500000
SITE POSSESSION
A1160 | Possetion of Site | 340000 | 340000
EARTH WORKS
A1030 | Clearing & Grabing | 600000 | 600000
A1040 | Cutting | 2400000 | 2400000
A1050 | Embankment Filling | 3000000 | 3000000
SUB-GRADE & SUB-BASE
A1000 | Subgrade & Subbase | 1000000 | 1000000
PAVEMENT
A1060 | Wearing Course | 1400000 | 1400000
STRUCTURES
A1070 | Viaducts | 2350000 | 2350000
A1080 | Box Culverts | 2350000 | 2350000
A1090 | Underpasses | 2350000 | 2350000
A1100 | Overpasses | 2350000 | 2350000
DRAINAGE
A1190 | Drainages | 1130000 | 1130000
INCIDENCIALS
A1120 | Incidencials | 4500000 | 4500000
HANDOVER
A1170 | Handover | 1000000 | 1000000

## HSE&Quality
HSE STATISTICS
|  | NCR |  |  |  | 2015-05-11
|  | Submitted |  |  |  | 160
|  | Open |  |  |  | 39
|  | Closed |  |  |  | 121
|  | SOR |  |  |  | 2015-05-11
|  | Submitted |  |  |  | 282
|  | Open |  |  |  | 75
|  | Closed |  |  |  | 207
NCR
|  | 160 | 160
|  | 39 | 39 | 24.38%
|  | 121 | 121 | 75.62%
SOR
|  | 282 | 282
|  | 75 | 75 | 26.6%
|  | 207 | 207 | 73.4%
HSE STATISTICS OF PROJECT TILL DATE
| Total Manhours |  |  |  | 1422500
| LTIFR |  |  |  | 0.14
| RIR |  |  |  | Nill
LTI
LTI
Fatalities
MTC
First Aid
Ill Health
Near Miss
Observation
LTI

## Manpower Curve
| w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w11 | w12 | w13 | w14 | w15 | w16 | w17 | w18 | w19 | w20 | w21 | w22 | w23 | w24 | w25 | w26 | w27 | w28 | w29 | w30 | w31 | w32 | w33 | w34 | w35 | w36 | w37 | w38 | w39 | w40 | w41 | w42 | w43 | w44 | w45 | w46 | w47 | w48 | w49 | w50 | w51 | w52 | w53 | w54
Week Ending | time axis 2017-02-01 to 2018-05-09
Baseline | 22 | 22 | 25 | 25 | 25 | 25 | 29 | 29 | 29 | 29 | 29 | 39 | 39 | 39 | 39 | 51 | 51 | 51 | 51 | 51 | 74 | 74 | 74 | 74 | 104 | 104 | 104 | 104 | 94 | 94 | 94 | 94 | 94 | 61 | 61 | 61 | 61 | 44 | 44 | 44 | 44
Actual | [15 empty] | 10 | 10 | 10 | 10 | 10 | 25 | 25 | 25 | 25 | 125 | 125 | 125 | 125 | 175 | 175 | 175 | 175 | 175 | 499 | 499 | 499 | 499 | 945 | 945 | 945 | 945 | 960 | 960 | 960 | 960 | 947 | 907 | 853 | 716 | 527 | 416 | 346 | 251 | 203 | 175 | 159

## Milestones
MILESTONE DATA |  | ACTUAL | MILESTONE DATA | PLAN | ACTUAL
PLAN
Project Start | 2017-02-01 |  | Project Start | 2017-02-01
Mobilization Completion | 2019-07-31 |  | Mobilization Completion | 2019-07-31
Possession of Site Completion | 2018-01-31 |  | Highway Design Completion | 2019-06-30
Highway Design Completion | 2019-06-30 |  | Structural Design Completion | 2018-07-31
Structural Design Completion | 2018-07-31 |  | Road Pavement Completion | 2019-07-14
Earthworks Completion | 2019-05-25 |  | Structures Completion | 2019-07-24
Subbase & Base Course Comletion | 2019-06-23 |  | Project Completion | 2019-07-31
Road Pavement Completion | 2019-07-14
Structures Completion | 2019-07-24
Project Completion | 2019-07-31